## JUN
Unsafe Act & Condition
Month of : OCT
Number of Unsafe Condition: 06 Number of Unsafe Act: 01
NO. | Unsafe Condition |  |  |  | Unsafe Act
1 |  | UC | The barricades are not interlocked, and there are noticeable gaps between the barriers, which may lead to potential fall hazards for animals and children living near the excavation area. There is no warning signboards installed around the excavation areas at the site, which may pose a safety risk to workers and nearby residents. | CLOSE |  | UA | The loading and arrangement of the barriers on the crane truck were done in a disorganized manner, which may cause instability and potential safety hazards during transportation. | CLOSE
2 |  | UC | The first aid box does not contain a checklist to monitor the availability and condition of medical supplies. | CLOSE |  | UA |  | CLOSE
3 |  | UC | No barriers have been provided around the rock breaker storage area, and the equipment has been placed randomly at the site without proper demarcation or organization. | CLOSE |  | UA |  | CLOSE
4 |  | UC | The first aid box has missing medical supplies, and no checklist is available to monitor and track the items regularly. | CLOSE |  | UA |  | CLOSE
5 |  | UC | No warning stickers or notices were placed on the houses in front of which the work is being carried out, and the barriers were not properly fixed/secured in place. | CLOSE |  | UA |  | CLOSE
6 |  | UC | The water thermos has not been placed under the shelter, leaving it exposed to direct sunlight and potential contamination. | CLOSE |  | UA |  | CLOSE
7 |  | UC |  | CLOSE |  | UA |  | CLOSE
8 |  | UC |  | CLOSE |  | UA |  | CLOSE
9 |  | UC |  | CLOSE |  | UA |  | CLOSE
10 |  | UC |  | CLOSE |  | UA |  | CLOSE